## Sheet1
Week | Date | Time | Duration | Activity
2 | 27.07.2020 | 16:30 | 1.5 | Meeting with supervisor
| 27.02.2020 | 20:00 | 0.5 | Meeting with group members
3 | 08.03.2020 | 18:10 | 0.3 | Meeting with supervisor
|  | 20:00 | 0.3 | Sprint 1 meeting
| 08.05.2020 | 17:00 | 1 | Look for interesting datasets
|  | 21:30 | 1.15 | Meeting with group members
| 08.06.2020 | 20:30 | 1.1 | Meeting with group members
|  | 22:30 | 0.2 | Creating gantt chart
| 08.09.2020 | 18:30 | 0.45 | Meeting with group members
4 | 08.10.2020 | 18:10 | 0.2 | Meeting with Supervisor
| 08.10.2020 | 20:00 | 0.45 | Meeting with group members
| 08.13.2020 | 20:00 | 0.45 | Reassessing research questions
| 08.15.2020 | 18:00 | 2.5 | Data Cleaning
| 08.16.2020 | 20:00 | 0.4 | Reassessing dara cleaning methods with team members
5 | 08.17.2020 | 18:00 | 0.3 | Meeting with supervisor
|  | 20:00 | 1 | Meeting with team members
| 08.23.2020 | 20:00 | 0.3 | Retro meeting with team
6 | 08.25.2020 | 20:00 | 1 | Meeting with team members
| 08.30.2020 | 20:00 | 1 | Retro meeting with team
| 08.28.2020 | 18:00 | 2 | Data Visualisation
7 | 09.07.2020 | 20:00 | 1.5 | Meeting with team members
8 | 09.17.2020 | 20:00 | 3 | Meeting with team members
| 09.19.2020 | 20:00 | 1 | Meeting with team members
| 09.20.2020 | 20:00 | 0.3 | Retro meeting with team
| 09.20.2020 | 16:00 | 3 | Creating random forest code for predictive analytics
9 | 09.22.2020 | 19:00 | 1 | Sprint planning meeting
| 09.23.2020 | 15:00 | 2 | Further research into random forest for predictive analysis
| 09.24.2020 | 19:00 | 2 | Optimizing random forest model for predictive analysis
| 09.27.2020 | 20:00 | 1 | Retro meeting with team
10 | 09.28.2020 | 20:00 | 1.5 | Sprint planning meeting
| 10.01.2020 | 10:00 | 1 | Report Writing for data cleaning
| 10.02.2020 | 16:00 | 1 | Report Writing for data Visualisation
| 10.04.2020 | 20:00 | 1 | Retro meeting with team
11 | 10.05.2020 | 20:00 | 1 | Sprint planning meeting
| 10.07.2020 | 15:00 | 2 | Report writing for data modelling
| 10.08.2020 | 16:00 | 1 | Report writing for data modelling
| 10.11.2020 | 20:00 | 1 | Retro meeting with team
12 | 10.12.2020 | 20:00 | 1.5 | Sprint planning meeting
| 10.13.2020 | 14:00 | 1 | Report writing on the conclusion part
| 10.14.2020 | 16:00 | 2 | Report writing on prescricptive analytics
| 10.17.2020 | 21:00 | 3 | Finalizing everything for submission
| 10.18.2020 | 20:00 | 1 | Retro meeting with team